## Sheet1
Creating Semantic Spaces Using Document Clustering Effort Matrix
Yahya Emara, Tristan Weger, Ryan Rubadue
Task | Ryan % Work | Tristan % Work | Yahya % Work | Rough Total Task Hours
Pick dataset to use | 50 | 25 | 25 | 3
Overview Entire code | 33 | 33 | 33 | 10
Create token parsing code | 25 | 50 | 25 | 20
Create token filtering network | 25 | 50 | 25 | 8
Embed tokens into high dimension semantic space | 25 | 25 | 50 | 10
Create code and network to cluster tokens | 25 | 25 | 50 | 10
Create a final tuned filter | 50 | 25 | 25 | 10
Create a cognitive map for 2D data | 25 | 25 | 50 | 10
Create a visual representation of ~50D data | 25 | 25 | 50 | 3
Prepare Final Presentation | 33 | 33 | 33 | 5
Determine what kind of machine learning method to use (supervised, reinforcement, unsupervised, transfer, etc.) | 25 | 50 | 25 | 3
Run the clustering algorithm using the different data subset partitions. | 25 | 50 | 25 | 3
Select a cross validation method to get a more accurate rating of the performance of each model | 25 | 50 | 25 | 2
Interpret the clustering results and make adjustments if needed. | 25 | 50 | 25 | 3
Determine optimal amount of vector space reduction that can be achieved without losing anything above minimal classification data. | 50 | 25 | 25 | 2.5
Decide methodology of dimension reduction and document rationale behind choice. | 50 | 25 | 25 | 3
Actual implementation of dimension reduction. | 50 | 25 | 25 | 7
Compare application results when reducing to different numbers of dimensions. | 50 | 25 | 25 | 4
Document if the optimal number of dimensions is relatively consistent across different document embedding techniques. | 50 | 25 | 25 | 2
Design quality and informative visualizations for reduced 2D vector space. | 50 | 25 | 25 | 2.5
Potential. Employ different method/tool in order to reduce dimensions. Convey whether results remain consistent or differ. | 50 | 25 | 25 | 5
Break document into word pairs | 25 | 25 | 50 | 5
Break document into sentences | 25 | 25 | 50 | 5
Filter data to keep relevant word tokens | 25 | 25 | 50 | 5
Embed tokens into high dimensionality semantic vectors | 25 | 25 | 50 | 10
Compare embedding methods and optimize using the best method | 25 | 25 | 50 | 5